## Summary
AgroSync Security & Code Audit
Audit date: 2026-10-05 · Scope: Laravel backend (routes, controller, middleware, config, migrations, seeders) and Next.js frontend auth/API layer · Method: static code review (no live exploitation)
Verdict: NOT SAFE TO DEPLOY — the API has no authentication; payment verification can be bypassed.
Severity | Total | Open | In Progress | Fixed | Won't Fix | % Fixed
Critical
High
Medium
Low
Total
How to use
Edit only the yellow columns on the Findings tab: Status (dropdown), Owner, Notes.
Counts on this tab update automatically from the Findings tab.
Fix order: 1) Sanctum auth 2) authorization/ownership 3) server-side payment verification 4) block admin self-registration
5) rate limits on login/OTP 6) input validation & field allow-lists 7) move env() to config, rotate secrets 8) remove mock fallback.

## Findings
ID | Severity | Category | Title | Location | Description | Impact | Recommendation | Status | Owner | Notes
C1 | Critical | Authentication | No authentication on any API route | backend/routes/api.php; backend/app/Http/Controllers/Api/AgroSyncController.php:798; ams-frontend/services/index.ts:64-70 | Only ApiCors middleware is applied. The login token is random, never stored and never checked. The frontend sends no Authorization header; the session is just a user ID in localStorage. | Anyone can call admin, payment, settlement and account-deletion endpoints directly with curl. | Add Laravel Sanctum; issue tokens at login/OTP verify; put auth:sanctum on all non-public routes; send a Bearer token from the frontend. | Fixed |  | Bearer-token auth (api_tokens table, AuthenticateApiToken middleware); frontend sends Authorization header.
C2 | Critical | Authorization (IDOR) | No ownership checks on any record | Whole controller (e.g. backend/app/Http/Controllers/Api/AgroSyncController.php:1106-1121, 3180) | Handlers trust farmerId/companyId/userId/officerId from the URL or body: DELETE /users/{id}, PATCH /users/{id}, settings, notifications, cart, products, listings, advisory responses. | Any user can read, modify or delete any other user's data, or respond to cases as any officer. | Add policies / role middleware; derive the acting user from auth()->user(), never from request IDs. | Fixed |  | Ownership checks on every user-scoped endpoint; RequireRole middleware on role routes.
C3 | Critical | Account takeover | Admin takeover via unverified email change + OTP login | backend/app/Http/Controllers/Api/AgroSyncController.php:547, 803-872 | PATCH /users/usr_adm_001 changes the email with no verification; send-otp then mails the login code to the new address. | Full takeover of any account, including Super Admin. | Require auth + ownership for profile edits; verify new email via OTP sent to the old and new address; check uniqueness. | Fixed |  | Profile edits are self/admin only; email change needs current password and a uniqueness check.
C4 | Critical | Payments | Payments can be faked | backend/app/Http/Controllers/Api/AgroSyncController.php:1360-1362, 1914, 2462, 2709, 2863 | Stripe success marks paid when session_id is empty; SSLCommerz success marks paid when status is empty/VALID without validation API; non-cod/stripe gateway marks order paid immediately; deal status update accepts paymentStatus from client. | Orders/deals marked paid without payment; admin then releases vendor settlement for unpaid orders. | Remove the empty-session bypass; verify via SSLCommerz validation API and Stripe webhook with signature check; never accept paymentStatus from clients. | Fixed |  | Stripe/SSLCommerz verified server-side against the stored session/tran id; orders always start unpaid; client paymentStatus ignored.
C5 | Critical | Privilege escalation | Self-registration as admin; unknown roles skip OTP | backend/app/Http/Controllers/Api/AgroSyncController.php:880-892 | register-role accepts role=admin from the client, needing only an OTP to the attacker's own inbox. Roles outside the list skip the OTP check. tenantId and id are client-controlled. | Anyone can become a platform admin. | Allow-list self-registerable roles (farmer, vendor, company); reject everything else; generate IDs and tenant server-side. | Fixed |  | Only farmer/officer/vendor/company can self-register; officers start inactive until an admin activates them.
C6 | Critical | Mass assignment | Every request key written as a DB column | backend/app/Http/Controllers/Api/AgroSyncController.php:1258, 3265 | updateProduct and updateTenant convert all request keys to columns. | Attackers can change vendor_id, id, tenant_id, rating, mrr, status etc. | Use explicit allow-lists of editable fields plus validation. | Fixed |  | Explicit field allow-lists for products and tenants.
C7 | Critical | Data exposure | Bulk PII leak from /users and /farmers | backend/app/Http/Controllers/Api/AgroSyncController.php:418-428, 988-1000 | Unauthenticated, unpaginated endpoints return every user's email, phone, nidHash and bKash account. | Mass personal-data disclosure. | Restrict to admins, paginate, and return only required fields. | Fixed |  | /users is admin-only; /farmers hides nidHash, bKash and email from non-admins.
H1 | High | Authentication | OTP brute force, email bombing, user enumeration | backend/app/Http/Controllers/Api/AgroSyncController.php:278-303, 803-847 | No attempt limit on verify-otp; otpToken optional (email alone works); 6-digit code valid 10 min. send-otp unthrottled and reveals whether an email exists. | Login as any user by brute-forcing OTP; inbox flooding; account enumeration. | Throttle routes; per-OTP attempt counter with lockout; require otpToken; generic responses. | Fixed |  | otpToken required and bound to the email; OTP dies after 5 wrong codes; send-otp no longer reveals accounts; throttled.
H2 | High | Authentication | Login brute force | backend/app/Http/Controllers/Api/AgroSyncController.php:776-801 | No throttling or lockout on /auth/login. | Password guessing against any account. | Apply throttle middleware and progressive lockout. | Fixed |  | Login throttled per IP and per email (429).
H3 | High | Credentials | Weak default passwords and published demo credentials | backend/app/Http/Controllers/Api/AgroSyncController.php:910; ams-frontend/services/index.ts:361-366; backend/database/seeders | Registration defaults to password123 with no minimum length; all seeded accounts use password123; frontend bundle ships DEMO_CREDENTIALS including admin. | Trivial access to seeded/admin accounts. | Require a password with a minimum length; never seed in production; remove DEMO_CREDENTIALS from production builds. | Fixed |  | Min 8-char passwords; demo seeders refuse to run in production; demo credentials only in mock mode.
H4 | High | Secrets / TLS | Committed SSLCommerz credentials; TLS verification disabled | backend/.env.example; backend/app/Http/Controllers/Api/AgroSyncController.php:2208-2209, 2270 | Store ID and password committed as defaults; payment request uses withoutVerifying(). | Credential exposure; man-in-the-middle on payment traffic. | Rotate credentials, remove defaults from code, re-enable TLS verification. | Fixed |  | Credentials removed from code and .env.example; TLS verification on. ROTATE the SSLCommerz sandbox credentials.
H5 | High | Configuration | env() called at runtime (breaks with config:cache) | backend/app/Http/Controllers/Api/AgroSyncController.php (multiple); backend/app/Http/Middleware/ApiCors.php | After php artisan config:cache, env() returns null: Stripe key empty (falls back to mock gateway + C4 bypass), FRONTEND_URL falls back to localhost in CORS, weather key ignored. | Production payments silently run in mock mode; CORS breaks. | Move all env() reads into config/services.php and use config() in code. | Fixed |  | All env() reads moved to config (services.php, app.php, agrosync.php, cors.php).
H6 | High | Business logic | Deal state machine bypassable | backend/app/Http/Controllers/Api/AgroSyncController.php:1873, 1931 | actorRole is client-supplied; same-status updates rewrite price, quantity and payment status at any stage. | Price/quantity changes after lock; fake paid status. | Derive actor role from the authenticated user; disallow edits after lock. | Fixed |  | Actor role comes from the token; price/qty only change during negotiation; gateway locked after payment.
H7 | High | Frontend | Silent mock fallback replaces the backend | ams-frontend/services/index.ts:52-55, 1448 | If NEXT_PUBLIC_API_URL is unset or unreachable, auth runs on mock data with hardcoded passwords and OTP 123456. | Misconfigured production deploy runs fake authentication. | Remove mock fallback in production builds; fail loudly instead. | Fixed |  | Mock fallback only when NEXT_PUBLIC_ENABLE_MOCK_API=true; otherwise errors surface.
H8 | High | Configuration | Debug mode and OTPs written to logs | backend/.env.example | APP_DEBUG=true and LOG_LEVEL=debug leak stack traces/SQL; MAIL_MAILER=log writes OTP codes to laravel.log. | Information disclosure; OTP leakage from logs. | APP_DEBUG=false in production; use a real mailer; never log OTPs. | Fixed |  | .env.example defaults: APP_DEBUG=false, LOG_LEVEL=info, MAIL_MAILER=smtp.
M1 | Medium | Validation | No input validation anywhere | Whole controller | $request->validate() / FormRequests never used. | Bad data, 500 errors, and the enabler for many issues here. | Add FormRequests for every write endpoint. | Fixed |  | Validator rules on all write endpoints.
M2 | Medium | Business logic | Order quantity/stock not validated; race conditions | backend/app/Http/Controllers/Api/AgroSyncController.php:1294-1305, 1357, 1398 | Negative quantities produce negative totals and increase stock; no stock check (overselling); no row locking; cart accepts negatives. | Financial and inventory corruption. | Validate quantity >= 1; check stock with lockForUpdate inside the transaction. | Fixed |  | Quantity 1..10000; stock checked under lockForUpdate; stock restored on cancel/return.
M3 | Medium | Business logic | Order status accepts any string from anyone | backend/app/Http/Controllers/Api/AgroSyncController.php:1426 | No allowed-status list or transition rules. | Orders can be pushed to arbitrary or invalid states. | Enforce allowed statuses and transitions per role. | Fixed |  | Per-role order transition table.
M4 | Medium | Data integrity | Partial profile update wipes data | backend/app/Http/Controllers/Api/AgroSyncController.php:561-600 | Omitted fields reset bkash_account, name_bn, land_size, crop_types, tags and districts to null/0/empty. | Users lose profile data on partial edits. | Only update fields present in the request. | Fixed |  | Only fields present in the request are written.
M5 | Medium | Data integrity | Email change not checked for duplicates | backend/app/Http/Controllers/Api/AgroSyncController.php:547 | Duplicate email hits the unique constraint. | 500 error instead of a clear message. | Validate unique:users,email except the current user. | Fixed |  | Duplicate email returns 422.
M6 | Medium | Correctness | Password change can silently do nothing | backend/app/Http/Controllers/Api/AgroSyncController.php:3149-3177 | User looked up by public or role ID, but update uses where public_id = $userId. | Returns success while the password is unchanged. | Update using $user->public_id. | Fixed |  | Update uses the resolved user's public_id; other sessions revoked.
M7 | Medium | Correctness | Collision-prone ID generation | backend/app/Http/Controllers/Api/AgroSyncController.php:891, 1586, 1220, 1737, 3244 | CRP-### allows only 999 listings; user IDs use count+1 (duplicates after deletion); tenant/product/deal IDs based on timestamp fragments. | Primary-key collisions and 500 errors as data grows. | Use UUIDs/ULIDs or auto-increment keys. | Fixed |  | Collision-checked random ids (uniqueId helper).
M8 | Medium | Data integrity | Orphan/junk records created | backend/app/Http/Controllers/Api/AgroSyncController.php:1581-1590, 1698 | createCropListing inserts listings for nonexistent farmers; expressInterest auto-creates company rows for any ID string. | Database pollution. | Reject requests for unknown entities. | Fixed |  | Unknown farmer/company rejected; no auto-created company rows.
M9 | Medium | Business logic | Crop interest skips farmer confirmation | backend/app/Http/Controllers/Api/AgroSyncController.php:1754 | expressInterest sets the deal straight to confirmed. | Farmer-confirmation step bypassed. | Create deals as pending. | Fixed |  | Interest creates a pending deal and notifies the farmer.
M10 | Medium | Abuse | Weather endpoint open to quota exhaustion | backend/app/Http/Controllers/Api/AgroSyncController.php:672-774 | Unauthenticated; calls a paid API and writes to the DB for any caller-supplied location. | API quota exhaustion and cache pollution. | Throttle; restrict to known districts; cache responses. | Fixed |  | Location validated; responses cached 30 min; route throttled.
M11 | Medium | Frontend | postMessage sent to '*' and origin not checked | backend/app/Http/Controllers/Api/AgroSyncController.php:3010; ams-frontend/components/dashboard/DashboardShell.tsx:147 | Payment popup broadcasts to any opener; listener does not check event.origin. | Info leak of deal/transaction IDs; spoofed payment events. | Post to the frontend origin; check event.origin in the listener. | Fixed |  | postMessage targets the frontend origin; listener checks event.origin.
M12 | Medium | Validation | No size limits on avatar/photos | backend/app/Http/Controllers/Api/AgroSyncController.php:74-85 | Avatar (TEXT column) and photo arrays accept strings of any size. | Storage exhaustion. | Use proper file uploads with size/type validation. | Fixed |  | Images must be http(s) or data:image URLs, max 2 MB, max 6.
L1 | Low | Performance | Per-row queries and no pagination | backend/app/Http/Controllers/Api/AgroSyncController.php (user(), order(), product(), deals) | Mappers run several queries per row; no list endpoint is paginated. | Slowdown and denial-of-service risk as data grows. | Use joins/eager loading and paginate every list. | In Progress |  | Per-request memo for repeated lookups in list mappers. Pagination not added (would change the API response shape).
L2 | Low | Maintainability | 3,476-line controller; Eloquent models unused | backend/app/Http/Controllers/Api/AgroSyncController.php | All logic in one controller with raw DB:: calls. | Hard to review, test and secure. | Split into per-domain controllers/services using the existing models. | Open |  | Not refactored: splitting the controller is a separate structural change.
L3 | Low | Correctness | Hardcoded fake admin metrics | backend/app/Http/Controllers/Api/AgroSyncController.php:3279-3304, 521-529 | uptime 99.98 and advisoryDeliveryRate 96.4 are constants; demo case IDs hardcoded into regional stats. | Misleading dashboards. | Compute real values or label them as placeholders. | Fixed |  | Fake uptime removed; delivery rate computed; demo case ids moved to config.
L4 | Low | Testing | No auth/authorization tests | backend/tests | Only 4 feature tests; none cover access control. | Regressions go unnoticed. | Add tests for every access rule as fixes land. | Fixed |  | 22 new security regression tests (tests/Feature/SecurityTest.php); suite 30/30 passing.
L5 | Low | Repo hygiene | Build artifact committed; duplicate env key | ams-frontend/tsconfig.tsbuildinfo; backend/.env.example | tsconfig.tsbuildinfo is committed; FRONTEND_URL defined twice. | Noise and confusion. | Git-ignore the artifact; remove the duplicate key. | Fixed |  | tsconfig.tsbuildinfo untracked and git-ignored; duplicate env key removed.
N1 | High | XSS | Reflected XSS in payment popup page | backend/app/Http/Controllers/Api/AgroSyncController.php (sslPaymentPopupResponse) | deal_id from the query string was embedded in a <script> block via json_encode(JSON_UNESCAPED_SLASHES), allowing </script> injection. | Script execution on the API origin via a crafted payment callback link. | Encode with JSON_HEX_TAG¦AMP¦APOS¦QUOT. | Fixed |  | Found while fixing C4; regression test added.